## Sheet1
Activity |  |  | Start Date | Finish Date | Duration (Days) | Responsible | Time | Task Status
1. Planning
| 1.1 | Share latest codes in r to all members | 2022-01-25 | 2022-01-26 | 1 | James
| 1.2 | Analysis team refresher for CPI | 2022-01-25 | 2022-01-26 | 1 | All | 2pm - 4pm
| 1.3 | Quality check on missing data using R | 2022-01-31 | 2022-02-11 | 11 | Vinau
| 1.4 | Boundary check by Eas | 2022-01-31 | 2022-02-11 | 11 | Alice
| 1.5 | Appending of the quartely data into the master spreadsheet (CPI_Stats) | 2022-01-25 | 2022-02-04 | 10 | James
| 1.6 | Calculate luganville price and weight aggregates | 2022-01-25 | 2022-02-11 | 17 | Vinau & Alice
| 1.7 | Discussion with CPI team on design draft 1 for CPI questionnaire in CAPI | 2022-01-31 | 2022-02-04 | 4 | All | 2pm - 5pm
2